## Five Buckets
MODULE 01 · BANKING · CAPITAL MARKETS
Sample — Junior Coordinator at a Capital Markets Ops Programme
A 9-month-in junior coordinator on a regulatory reporting platform replacement.
# | Bucket | What it means | Score | Trend | Evidence on this project
01 | Reliability | If you say you'll do something, it gets done — on time, to standard. | 4 | ↑ | Status reports go on Friday EOD without fail. Vendor cutover plan delivered 1 day early.
02 | Signal clarity | When you communicate, people know what's true, what matters, what to do. | 3 | → | Status narratives sometimes bury risks under green-amber-red without explaining absorption.
03 | Pattern recognition | You notice things before they blow up — slips, drift, friction. | 3 | → | Caught the SME availability slip 2 weeks early. Missed a vendor staffing gap that surfaced in the September SC.
04 | Judgment under ambiguity | You act well when instructions are incomplete. | 2 | ↓ | Tend to wait for explicit instruction on regulatory questions; could route more proactively to compliance.
05 | Cumulative trust | Built by every small thing done well over time. | 3 | ↑ | PM has begun delegating SC pre-reads. Sponsor has asked for me on the next initiative.
Pick one bucket. Just one. Work it for 30 days.
| My pick: | Judgment under ambiguity
| Why: | The compliance routing pattern is costing time. I want to default to action when instructions are incomplete.

## Inbox Audit
MODULE 01 · BANKING · CAPITAL MARKETS · TUESDAY
15-Minute Inbox Audit
Pattern from a real Tuesday morning on this project.
# | From (name / role) | What they're asking | Action implied? | Response time | What this reveals
01 | Compliance Lead · Marie Dube | Whether ISDA changes affect our Q4 release | Yes — clarify or route | 4 hours | Compliance routes through me too often
02 | Vendor PM · J. Park (Quantix) | Confirmation of UAT environment access for analyst team | Yes — coordinate access | Same day | Vendor still treats me as the gatekeeper
03 | Sponsor's EA | Reschedule SC by 3 days | Yes — re-circulate invite | 30 min | EA channel is reliable
04 | Internal audit | Review of decision log entries Aug–Sep | Information request | Same day | Audit window approaching
05 | Treasury (cc) | Funding allocation re-baseline question | No — informational | — | Mostly noise on copy line
06 | Risk Lead | Quantix counterparty risk question | Route to PM | 1 hour | Beyond my level — clean handoff

## Role Clarity
MODULE 01 · BANKING · CAPITAL MARKETS
Coordinator Role — Self-Placement
Three coordinator roles. Knowing yours matters more than the title.
Role | What it covers | Ceiling | Are you in this one? (notes)
Administrative | Logistics, scheduling, document libraries, attendance, formatting. | Senior coordinator / project administrator | No — too narrow for what I'm doing day-to-day.
Hybrid analyst | All admin work + status reports, RAID log, change requests, working-level meetings. | Project manager | YES — this is me. Status reports, RAID log, change requests, dashboards.
Aspiring-PM | In practice running a workstream with a coordinator title. | Project manager (faster track) | Sometimes. I run the analyst-readiness workstream end-to-end, but with PM oversight on regulatory calls.