## Stated vs Actual
MODULE 06 · BANKING · OSFI-OVERSEEN
Sample — Capital Markets Risk Platform Replacement
$80M programme. Strong PMO. OSFI / FRTB regulatory pressure.
# | Governance item | STATED | ACTUAL (observed) | Gap
01 | Sponsor's role | Group CRO approves at SC. | CRO and Head of Trading pre-align. SC approves what they've agreed. | LARGE
02 | Steering committee shape | Decision-making body of 9. | Ratifying. CRO arrives with the decision. Others ask questions, rarely change outcomes. | LARGE
03 | RACI Accountability for budget | CRO + CFO + Head of Trading (3 names). | CRO is the actual decider; others are consulted. | LARGE — diffuse
04 | How risks escalate | Through PMO to ERMC. | Directly via Risk Director's standing weekly with CRO. | Some
05 | How regulatory items flow | Through Compliance to SC. | Compliance Director has direct line to CRO; Compliance Lead works through her. | Some
06 | Side-channel access | Per RACI no side channels. | Trading desk heads have ad-hoc access to CRO. | LARGE
07 | PMO authority | Mandate to enforce reporting standards. | Has teeth — late reports trigger escalation. | None
08 | Whose assessments shape the CRO | Per RACI: SC + PMO. | Risk Director + Compliance Director + Head of Trading. | Some

## Stakeholder Map
MODULE 06 · BANKING · OSFI-OVERSEEN
Stakeholder Map — sample
Influence × Engagement on this project.
# | Name / role | Influence | Engagement | What they care about; who they trust
01 | Group CRO | H | M | Capital ratios, OSFI relationship, internal audit.
02 | Risk Director | H | H | Daily risk operations. CRO's trusted lieutenant.
03 | Compliance Director | H | H | Regulatory exposure. Direct line to CRO.
04 | Head of Trading (front office) | H | M | Trader productivity, P&L impact of platform.
05 | CFO | M | L | Programme cost, financial reporting impact.
06 | Programme Director (PMO) | M | H | Schedule, gating, status quality.
07 | Internal Audit | M | M | Control evidence.
08 | Vendor Lead | M | H | Delivery and SLA performance.
09 | OSFI Liaison | H | L | External regulatory satisfaction.
10 | External Auditor | M | L | Year-end audit findings.

## Sponsor Diagnostic
MODULE 06 · BANKING · OSFI-OVERSEEN
Sponsor Type — Diagnosis
Sample diagnosis on this project.
# | Type | Symptoms observed | Counter-move you're using
01 | Good | Owns outcome. Has authority. Engaged but not micromanaging. | ✓ Mostly — but CRO is over-engaged on trading-desk concerns. Manage with structured weekly briefing.
02 | Absent | Named on charter. Attends no meetings. | —
03 | Weak | Attends but defers. No real political capital. | —
04 | Over-engaged | Micromanages decisions that should be the PM's. | Mild — over-engaged when traders complain. Counter: structured weekly to absorb the energy.
05 | Wrong-level | Too junior for the political weight required. | —
06 | Misaligned | Personally invested in a different outcome. | —

## RACI Audit
MODULE 06 · BANKING · OSFI-OVERSEEN
RACI Audit — sample
Decisions on this project. Note where Accountable has more than one name (issue!).
# | Decision / deliverable | R | A | C | I | Issue?
01 | Approve programme charter | PM | Group CRO | CFO, Head of Trading | ERMC
02 | Approve budget changes | PM | CRO + CFO + HoT | PMO | Audit Cmte | Y — three A; CRO is real decider
03 | Approve scope changes | PM | Risk Director | Compliance Director | PMO
04 | Approve risk acceptance | Risk Lead | Risk Director | Compliance, IA | CRO
05 | Sign off regulatory artefacts | Compliance Lead | Compliance Director | Legal, IA | OSFI Liaison
06 | Approve vendor changes | Procurement | Group CRO | Vendor Mgmt, IA | PMO
07 | Approve go-live | PM | Group CRO | Head of Trading, Compliance Director | ERMC, OSFI Liaison