## Phase Map
MODULE 02 · CONSTRUCTION · INFRASTRUCTURE
Sample — Light Rail Station Build
A C$280M station expansion project. Heavy waterfall frame.
# | Phase | Coordinator's primary task | Key artifact | Next gate / milestone | AI / info-mgmt guardrail
01 | Initiation | Confirm authority-to-proceed. Identify utilities, environmental, indigenous consultation contacts. Set up controlled drawings repository. | Project Charter (signed) | Authority to commence detailed design | All drawings routed via DMS. No external file-sharing.
02 | Planning | Establish WBS at deliverable level. Set up RFI tracker, change order log, RAID. Prepare contractor coordination cadence. | WBS · Master schedule · RAID | Plan Baseline approval (PMO + sponsor) | Schedule lives in P6. No copies in email.
03 | Execution | Track RFIs, contractor submittals, NCRs. Run weekly construction meeting. Maintain field updates. | RFI log · Submittal log · Daily reports | Substantial completion at 50% structure | Photos and field reports stored controlled — privacy of workers.
04 | Monitoring | Compare earned value to baseline. Track unresolved NCRs. Surface schedule float consumption. | EVM report · NCR ageing · Float burn | Mid-project sponsor review | Burn-down dashboards reconciled to source of truth weekly.
05 | Closing | Coordinate punch list close-out. Archive as-builts. Capture lessons. Hand over to operations and warranty. | As-builts · O&M manuals · Lessons | Service-readiness gate | Archive controlled versions. No screenshots in close-out folder.

## Gate Evidence
MODULE 02 · CONSTRUCTION · INFRASTRUCTURE · GATES
Evidence Required at Each Gate
What the governance body needs in order to make the next decision.
# | Gate | Evidence required | Owner | Status / notes
G01 | Authority to proceed | Charter, business case, environmental approvals, funding confirmation | Sponsor + PMO | Cleared Q1
G02 | Design baseline | Detailed design package, cost plan, schedule, risk register | PM + Design lead | Cleared end Q2
G03 | Contractor mobilisation | Signed prime contract, insurance certs, safety plan | Procurement + PM | Cleared Q3
G04 | Substantial completion | Inspection certificate, punch list ≤ 5%, building permit | City inspector | Pending
G05 | Service readiness | O&M handover, training, warranty plan | Operations + PM | Pending