## Phase Map
MODULE 02 · PUBLIC SECTOR · REGULATORY
Sample — Provincial Tax Filing System Rebuild
A 24-month, $40M public-sector programme. Strict gating, multi-stakeholder oversight.
# | Phase | Coordinator's primary task | Key artifact | Next gate / milestone | AI / info-mgmt guardrail
01 | Initiation | Confirm legislative mandate, business case sign-off, deputy minister sponsor. Identify privacy commissioner and OAG touchpoints. | TB Charter · Privacy Impact Assessment scope | Treasury Board approval | Citizen data NEVER in unsanctioned tools. PIA must precede storage decisions.
02 | Planning | Build WBS at deliverable level. Set up gating model. Identify all assurance reviews required (security, privacy, accessibility, OAG) | Plan baseline · Gating plan | Gate 1 — Plan baseline | Source of truth: GCdocs. Drafts in Teams; controlled docs only in GCdocs.
03 | Execution | Drive vendor delivery. Maintain assurance evidence pack. Coordinate departmental SME availability. Track briefing notes. | Status updates · Briefing notes · Defects | Gate 2 — Build complete | Briefings to minister's office require fact-check; never AI-drafted.
04 | Monitoring | Run gating reviews. Variance reporting. Escalate to Project Leadership Committee. Manage independent reviewer findings. | EVM · Gate evidence pack · IR responses | Gate 3 — Service readiness | Independent review evidence kept under change control.
05 | Closing | Hand over to ops, training, citizen services. Final OAG audit submission. PIR (post-implementation review). | Operational handover · Lessons · OAG submission | Gate 4 — Closure | Archive per Library and Archives Canada retention schedule.

## Gate Evidence
MODULE 02 · PUBLIC SECTOR · REGULATORY · GATES
Evidence Required at Each Gate
What the governance body needs in order to make the next decision.
# | Gate | Evidence required | Owner | Status / notes
G01 | Treasury Board approval | Charter, business case, options analysis, indigenous consultation summary | Treasury Board | Cleared
G02 | Plan baseline (Gate 1) | Detailed plan, risk register, PIA, security assessment | Project Leadership Committee | Cleared
G03 | Build complete (Gate 2) | Code complete, security cert, accessibility cert, training plan | PLC + Privacy Comm. | Active
G04 | Service readiness (Gate 3) | End-to-end test results, ops handover, citizen services plan | Deputy Minister | Pending
G05 | Closure (Gate 4) | Benefits realisation, OAG audit, PIR | Treasury Board | Pending