## Fit Diagnostic
MODULE 05 · METHODOLOGY FIT
The Four Questions
Score this project on each axis 1–5. Lean waterfall (left) ↔ Lean agile (right). The work drives the answer.
# | Question | Lean ← | Score 1–5 | Notes / evidence
01 | How stable is the scope? | Stable=1 → Emergent=5
02 | How expensive is mid-flight change? | Cheap=1 → Expensive=5 (reverse this in your reading)
03 | How interdependent is the work? | Self-contained=5 → Coordinated=1
04 | What governance does the environment require? | Lightweight=5 → Heavy=1
Verdict
Average score:
| Recommended posture: | Pure waterfall / Hybrid waterfall-leaning / Hybrid agile-leaning / Pure agile
What this means in practice:

## Failure Spot-Check
MODULE 05 · 5 FAILURE MODES
Spot the Pattern
On your current project — is any of this happening? Mark Y/N. Add evidence. Decide what to do.
# | Failure mode | Symptoms to look for | Y / N | Evidence on this project
01 | Waterfall theatre | Schedule exists but not used. RAID log updated but no one acts. CRs rubber-stamped.
02 | Agile theatre | Sprints, POs, retros — but no real discipline. Backlog is a wishlist. Increments not shippable.
03 | Methodology mismatch | Exploratory product run as waterfall. Regulatory programme run as Scrum.
04 | Hybrid without translation | Sprint outputs never aggregate up. PMO formats never reach the team.
05 | Methodology as excuse | "Can't give a deadline because we're agile." "Can't accommodate because PMO process." Cover for priority conversations.

## Translation Map
MODULE 05 · COORDINATOR AS TRANSLATOR
What gets translated where?
On a hybrid project, list the artifacts that flow between agile workstreams and waterfall governance — and who owns the translation.
# | Source artifact (agile) | Destination format (PMO) | Translation owner / cadence
e1 | Sprint review outputs | Monthly status report | Coordinator · monthly
e2 | Burndown / velocity | Schedule variance section | Coordinator · weekly
e3 | Retro outputs (risks) | RAID log | Coordinator · post-retro
e4 | Backlog refinement | Scope change requests | PO + Coordinator · ad hoc
e5 | Definition of Done | Phase gate criteria | PM + Coordinator · per gate
01
02
03
04
05
06
07
08