## Fit Diagnostic
MODULE 05 · PHARMA · REGULATED
Sample — Pharma Clinical Trial Software Build
Validated GxP environment. FDA / Health Canada / EMA scrutiny. Hybrid weighted heavily toward waterfall.
# | Question | Lean ← | Score 1–5 | Notes / evidence
01 | How stable is the scope? | Stable=1 → Emergent=5 | 2 | Scope is defined by validated requirements; emergent only in UI/UX details.
02 | How expensive is mid-flight change? | Cheap=5 → Expensive=1 | 1 | Mid-flight changes trigger re-validation cycles — extremely expensive.
03 | How interdependent is the work? | Self-contained=5 → Coordinated=1 | 2 | Tightly coordinated with QA, regulatory, statistical computing.
04 | What governance does the environment require? | Lightweight=5 → Heavy=1 | 1 | 21 CFR Part 11, GxP, ISO 13485 audit-ready governance required.
Verdict
| Recommended posture: | Hybrid heavily weighted to waterfall: predictive frame, time-boxed agile only inside UI workstreams; all validation activities are gated.

## Failure Spot-Check
MODULE 05 · PHARMA · REGULATED
Five Failure Modes — Findings
Findings on this real project.
# | Failure mode | Symptoms — what you'd look for | Y / N | Evidence on this project
01 | Waterfall theatre | Schedule exists but not used. RAID log updated but no one acts. | N | Schedule and RAID are used in every steering. Decisions taken on the data.
02 | Agile theatre | Sprints, POs, retros — but no real discipline. | Y | UI team runs sprints but the 'increment' has not been independently validated for two sprints — agile theatre risk.
03 | Methodology mismatch | Wrong approach for the work. | N | Methodology fit is appropriate; no mismatch.
04 | Hybrid without translation | Sprint outputs never aggregate up; PMO formats never reach team. | Y | Sprint outputs not consistently rolled up into validation-ready evidence packs. Translation gap — coordinator filling.
05 | Methodology as excuse | "Can't give a deadline because we're agile." | N | No excuses observed.

## Translation Map
MODULE 05 · PHARMA · REGULATED
Translation between Agile and Governance
Real artifacts that flow between layers on this project.
# | Source artifact (agile) | Destination format (governance) | Translation owner / cadence
01 | Sprint review demo (UI) | Validation evidence appendix | Coordinator + QA · per sprint
02 | Backlog refinement notes | Requirements traceability matrix | BA + Coordinator · weekly
03 | Burn-up (sprint-level) | Programme-level milestone variance | Coordinator · weekly
04 | Retro outputs (process) | Quality system CAPA log | QA + Coordinator · post-retro
05 | Definition of Done (UI) | Phase gate criteria — UI signoff | PM + QA · per gate