## Five Variables
MODULE 07 · RETAIL · CUSTOMER-FACING PLATFORM
Sample — Loyalty Platform Build (the chapter's case study)
$8M, 12-month deadline tied to a board commitment. Sponsor declared all three corners fixed.
# | Variable | What you'd flex first if pressure came | Flex remaining | Already committed | Evidence / notes
01 | Scope | Drop two non-core brand integrations (already done implicitly) | L | H | Sponsor declared scope fixed; non-core integrations were cut without being named in change log
02 | Schedule | 3 weeks left in plan; 0 explicit contingency | L | H | Schedule contingency was removed by sponsor as 'padding'
03 | Cost | $200K vendor budget unspent | L | H | Budget fixed by sponsor; one minor vendor reserve still available
04 | Quality | UAT scope on non-core flows reduced from 85% to 60% | L | H | Pressure absorbed silently into testing — the chapter's central failure mode
05 | Risk | 3 high-impact risks unmitigated; flex used | L | H | Authentication risk + POS risk + data residency risk all unresolved

## Scope Triple
MODULE 07 · RETAIL · CUSTOMER-FACING PLATFORM
Scope — three kinds, with the gap
Watch the gap between documented scope and what the sponsor actually expects.
# | PRODUCT scope | PROJECT scope (team will do) | SPONSOR'S head
01 | Loyalty engine — earn / burn / tier | Build, integrate with 3 POS systems, training | All-stores live, board-narrative ready, mobile-first experience
02 | Customer mobile app | Build, app-store submission | Crash-free, 4.5+ star rating, retention-driving
03 | Data warehouse integration | ETL build only — analyst dashboards out of scope | Full BI dashboards by launch (NOT in documented scope)
04 | Customer support tooling | Existing systems integration | New CSAT-driving experience for agents (NOT in scope)

## Risk Mapping
MODULE 07 · RETAIL · CUSTOMER-FACING PLATFORM
Risk → Variable mapping
For each risk, which of the five variables would absorb it. Plus the absorption strategy.
# | Risk | Variable threatened | Mitigation | Absorption strategy
R01 | POS integration complexity (3 brands, 2 with custom configs) | Schedule + Quality | Cataloguing in week 6; vendor walkthrough | Schedule slip OR test-coverage cut on non-core
R02 | Authentication library licensing flagged late by procurement | Schedule + Quality | Legal review in week 14 | Accept fallback security pattern (we did) — quality cut
R03 | Data residency requirement surfaced by compliance review | Cost + Schedule | Architecture rework decision needed | Weekend rework absorbed silently — quality cut
R04 | UAT compressed by 3 weeks | Quality | Reduce non-core test coverage | Post-launch defect risk on non-core flows
R05 | Vendor key resource on parental leave Oct 1–Dec 1 | Schedule | Backup resource identified | Schedule slip if backup ramp-up exceeds 4 weeks

## Contingency Burn
MODULE 07 · RETAIL · CUSTOMER-FACING PLATFORM
Contingency Burn — sample
A project burning contingency faster than it burns work is a project where contingency is about to run out.
# | Month | Schedule original | Schedule used | Cost original | Cost used | Notes
M01 | Month 1 | Schedule: 2 wk | 0 | $300K | $30K | On plan
M02 | Month 2 | Schedule: 2 wk | 0.5 wk | $300K | $80K | POS discovery — early use of buffer
M03 | Month 3 | Schedule: 1.5 wk | 1.0 wk | $300K | $120K | Continued POS discovery
M04 | Month 4 | Schedule: 0.5 wk | 1.5 wk | $300K | $170K | Compliance issue surfaced — accelerated burn
M05 | Month 5 | Schedule: 0 wk | 2.0 wk | $300K | $240K | OUT OF SCHEDULE CONTINGENCY
M06 | Month 6+ | — | Quality cuts begin | — | $300K hard limit | Silent absorption into quality