## RAID log
ID | Type | Description | Trigger | Impact | Likelihood | Mitigation | Owner | Follow-up | Status
R-001 | Risk | Might miss deadline |  | Bad | Medium | Watch closely |  |  | Open
R-002 | Risk | Vendor issues |  |  |  | Monitor |  |  | Open
I-001 | Issue | Scope changed |  |  |  | Talk to PM |  |  | Open

## Instructions
Field | What goes here
ID | R-001, I-001, A-001, D-001... Use the letter prefix to make the Type obvious even in a quick scan.
Type | One of: Risk (might happen), Issue (already happened), Assumption (taken for granted), Dependency (external blocker).
Description | What specifically could go wrong or has gone wrong. One sentence. Use project-specific nouns — 'the vendor API', not 'the integration'.
Trigger | The observable event that would move this from theoretical to real. 'Vendor announces deprecation date', 'Sprint 3 ends without sign-off', etc.
Impact | What concretely breaks or slips if this risk fires. Quantify when possible — days, dollars, SLAs.
Likelihood | Low / Medium / High. Keep it simple; probability maths isn't the point.
Mitigation | The actual action being taken — not 'monitor'. 'Backfill lead engineer from contractor pool', 'Draft v2 migration plan by Sprint 4', etc.
Owner | Named role (Tech Lead) or named person (Jordan). Never blank.
Follow-up | Date you'll check this item again. Every open item has one.
Status | Open → In progress → Mitigated → Closed. A RAID log is a living artifact; update status weekly.