## Five Variables
MODULE 07 · POSTURE
The Five-Variable Posture
For each variable: how much flex is left, how committed it is, evidence on this project. Private assessment.
# | Variable | What you'd flex first if pressure came | Flex remaining (H/M/L) | Already committed (H/M/L) | Evidence / notes
01 | Scope | What scope items would go first if pressure rose?
02 | Schedule | How much schedule contingency remains?
03 | Cost | How much budget contingency remains?
04 | Quality | Where is the quality bar already pressured?
05 | Risk | What's the remaining risk envelope?

## Scope Triple
MODULE 07 · SCOPE
The Three Scopes
For each scope question on your project, capture what's documented vs what the sponsor seems to expect. Look for the gap.
# | PRODUCT scope (features/functions) | PROJECT scope (what team will do) | SPONSOR'S head (unspoken expectations)
Item 01
Item 02
Item 03
Item 04
Item 05
Item 06
Item 07
Item 08

## Risk Mapping
MODULE 07 · RISK MAPPING
Each risk → which variable it threatens
For your top 10 risks, name which of the five variables would absorb the impact. Rewrite vague entries with explicit absorption strategy.
# | Risk | Variable threatened | Current mitigation | Absorption strategy if it materialises
R01
R02
R03
R04
R05
R06
R07
R08
R09
R10

## Contingency
MODULE 07 · CONTINGENCY
Contingency Burn Tracker
Track contingency consumption month by month. A project burning contingency faster than it burns work is one where contingency is about to run out.
Month | Schedule original | Schedule used | Cost original | Cost used | Notes
M01
M02
M03
M04
M05
M06
M07
M08
M09
M10
M11
M12