## Stated vs Actual
MODULE 06 · GOVERNANCE MAP
Stated vs Actual
For each item, capture the formal/stated structure on the left, what you've actually observed on the right, and the gap.
# | Governance item | STATED (per documents) | ACTUAL (per observation) | Gap
01 | Sponsor's role
02 | Steering committee shape
03 | RACI — Accountable for major decisions
04 | How budget changes get approved
05 | How scope changes get approved
06 | How risks get escalated
07 | Who briefs the sponsor before SC meetings
08 | Who has side-channel access to the sponsor
09 | How political concerns surface
10 | Whose questions get answered substantively in meetings

## Stakeholder Map
MODULE 06 · STAKEHOLDERS
Influence vs Engagement
For each named stakeholder, mark influence level and engagement level. The map tells you where to invest your relationship time.
# | Name / role | Influence (H/M/L) | Engagement (H/M/L) | Notes — what they care about, who they trust
01
02
03
04
05
06
07
08
09
10
11
12
13
14
15

## Sponsor Diagnostic
MODULE 06 · SPONSOR DIAGNOSTIC
Which kind do you have?
Mark the type. List the symptoms you're seeing. Decide your counter-move.
# | Type | Symptoms / what you're observing | Your counter-move this month
01 | Good | Owns outcome. Has authority. Engaged but not micromanaging. Has political capital.
02 | Absent | Named on charter. Attends no meetings.
03 | Weak | Attends but defers. No real political capital.
04 | Over-engaged | Micromanages decisions that should be the PM's.
05 | Wrong-level | Too junior for the political weight required.
06 | Misaligned | Personally invested in a different outcome.

## RACI Audit
MODULE 06 · RACI
RACI Audit
For each major decision type on your project, name who's R, A, C, I. Flag the rows where Accountable has more than one name.
# | Decision / deliverable | R | A | C | I | Issue?
01 | Approve project charter
02 | Approve budget
03 | Approve scope changes
04 | Approve major risks accepting
05 | Sign off phase gates
06 | Approve vendor selection
07 | Approve final delivery / go-live
08 | Decide on schedule slip > 2 weeks
09 | Approve change requests
10 | Approve resource changes