## Stated vs Actual
MODULE 06 · PUBLIC SECTOR · PROVINCIAL PROGRAMME
Sample — Provincial Tax-System Build
Deputy minister sponsor. Multi-stakeholder steering. Political dynamics constant.
# | Governance item | STATED | ACTUAL (observed) | Gap
01 | Sponsor's role | Deputy Minister approves all major decisions in steering. | Real decisions made in 30-min pre-briefings between deputy and chief of staff. | LARGE
02 | Steering committee shape | Decision-making body of 7 with all major decisions taken in the room. | Ratifying body. Decisions pre-agreed. Minutes use 'the Committee agreed' language. | LARGE
03 | RACI Accountability for major decisions | Steering committee | Deputy alone, after CoS briefing. | LARGE
04 | Political concerns flow | No formal mechanism in charter. | Standing weekly call between minister's adviser and CoS — never minuted. | LARGE
05 | How budget changes are approved | Treasury Board re-baseline. | Same — but pre-cleared by deputy informally before going formal. | Some
06 | How risks escalate | Through PMO to PLC. | Direct to deputy via CoS for politically sensitive items. | LARGE
07 | Whose questions get answered | All committee members per RACI. | Three of seven get substantive answers; others get deflections. | LARGE
08 | Side-channel access | None documented. | CPO has standalone monthly with the deputy. | LARGE
09 | Whose assessments shape the deputy | Per RACI: SC + PMO. | CoS + senior ADM + minister's adviser. Two of these are not on the committee. | LARGE

## Stakeholder Map
MODULE 06 · PUBLIC SECTOR · PROVINCIAL PROGRAMME
Stakeholder Map — sample
Influence × Engagement on this project.
# | Name / role | Influence | Engagement | What they care about; who they trust
01 | Deputy Minister | H | M | Career risk; minister's confidence. Trusts CoS.
02 | Chief of Staff | H | H | Briefing quality. Trusts the senior ADM and PM.
03 | ADM (operations) | H | H | Operational continuity. Has deputy's trust.
04 | ADM (policy) | M | M | Policy implications. Less day-to-day.
05 | Minister's Adviser | H | L (silent) | Political optics. Listens more than speaks.
06 | Privacy Commissioner Office | H | M | PIA quality, citizen data handling.
07 | Independent Reviewer | M | H | Risk and assurance findings.
08 | Programme Director (PMO) | M | H | Process compliance, gating.
09 | Vendor PM | M | H | Delivery and commercial terms.
10 | Treasury Board Secretariat | H | L | Funding and benefits realisation.

## Sponsor Diagnostic
MODULE 06 · PUBLIC SECTOR · PROVINCIAL PROGRAMME
Sponsor Type — Diagnosis
Sample diagnosis on this project.
# | Type | Symptoms observed | Counter-move you're using
01 | Good | Owns outcome. Has authority. Engaged but not micromanaging. | ✓ Match — but only when CoS pre-briefs him. Without it, more weak.
02 | Absent | Named on charter. Attends no meetings. | —
03 | Weak | Attends but defers. No real political capital. | —
04 | Over-engaged | Micromanages decisions that should be the PM's. | —
05 | Wrong-level | Too junior for the political weight required. | —
06 | Misaligned | Personally invested in a different outcome. | Mild — deputy's actual interest is partly being seen as a delivery DM. Consistent with the org outcome — flag if it diverges.

## RACI Audit
MODULE 06 · PUBLIC SECTOR · PROVINCIAL PROGRAMME
RACI Audit — sample
Decisions on this project. Note where Accountable has more than one name (issue!).
# | Decision / deliverable | R | A | C | I | Issue?
01 | Approve project charter | PM | Deputy | ADM, CoS | PMO
02 | Approve budget changes >$1M | PM | Deputy | Treasury Board liaison, CoS | PLC
03 | Approve scope changes | PM | PLC + Deputy | ADM, BA Lead | PMO | Y — multiple A; clarify
04 | Approve risk acceptance | Risk Lead | PM + Deputy | PLC | PMO | Y — multiple A; clarify
05 | Sign off phase gates (Gate 1–4) | PM | PLC Chair | Deputy, PMO | OAG liaison
06 | Approve vendor selection | Procurement | Deputy | ADM, PM | Treasury Board
07 | Approve final go-live | PM | Deputy | Privacy Comm., PLC | Minister's office