## Stated vs Actual
MODULE 06 · STARTUP · FOUNDER-LED
Sample — Series B SaaS — Billing Platform Replacement
35 engineers. Founder is sponsor. Lean governance. Reading what's real matters more.
# | Governance item | STATED | ACTUAL (observed) | Gap
01 | Sponsor's role | Founder approves through weekly 1:1. | Founder approves in Slack message — within 5 minutes most of the time. | Some
02 | Steering committee shape | Doesn't exist as a formal entity. | Founder + VP Eng + CFO biweekly check-in plays the role. | Some
03 | RACI Accountability | No formal RACI exists. | Founder for big calls; PM for trade-offs; Eng Lead for technical. | None — unwritten but clear
04 | How risks escalate | No formal escalation path. | PM Slack direct to founder when needed. | None
05 | Whose assessments shape founder | VP Eng officially. | VP Eng + CFO + senior advisor (board member). | Some
06 | PMO | Doesn't exist. | Coordinator (you) is the de facto PMO. | None
07 | Investor signals | Not a governance touchpoint. | Board updates pull schedule and risk into investor narrative — affects delivery posture. | Some
08 | Customer impact governance | Customer success informally. | CS lead has informal veto on customer-facing changes. | Some

## Stakeholder Map
MODULE 06 · STARTUP · FOUNDER-LED
Stakeholder Map — sample
Influence × Engagement on this project.
# | Name / role | Influence | Engagement | What they care about; who they trust
01 | Founder / CEO | H | M | ARR, growth narrative, board view.
02 | VP Engineering | H | H | Engineering velocity and team morale.
03 | CFO | M | M | Burn, ARR impact, board reporting.
04 | Customer Success Lead | M | H | Top-50 customer experience.
05 | Board lead investor | H | L (board only) | Burn rate, growth metrics, founder confidence.
06 | Senior advisor | M | M | Founder's ear on strategic decisions.
07 | Eng Manager (billing) | M | H | Daily delivery, team sanity.
08 | Sales Ops | L | M | Customer commitment cadence.

## Sponsor Diagnostic
MODULE 06 · STARTUP · FOUNDER-LED
Sponsor Type — Diagnosis
Sample diagnosis on this project.
# | Type | Symptoms observed | Counter-move you're using
01 | Good | Owns outcome. Has authority. Engaged but not micromanaging. | —
02 | Absent | Named on charter. Attends no meetings. | —
03 | Weak | Attends but defers. No real political capital. | —
04 | Over-engaged | Micromanages decisions that should be the PM's. | ✓ Match — founder is over-engaged. Counter: structured weekly briefing absorbs the need to be involved without dictating.
05 | Wrong-level | Too junior for the political weight required. | —
06 | Misaligned | Personally invested in a different outcome. | —

## RACI Audit
MODULE 06 · STARTUP · FOUNDER-LED
RACI Audit — sample
Decisions on this project. Note where Accountable has more than one name (issue!).
# | Decision / deliverable | R | A | C | I | Issue?
01 | Approve major scope changes | PM | Founder | VP Eng, CFO | Board (informational)
02 | Approve budget overruns | PM | CFO | Founder | Board
03 | Approve customer-impacting changes | PM | VP Eng + CS Lead | Founder | Sales Ops | Y — two A; clarify
04 | Approve technical architecture | Tech Lead | VP Eng | Founder, Senior Advisor | Eng team
05 | Approve go-live | PM | Founder | VP Eng, CS Lead, CFO | Board, customers