## Phase Map
MODULE 02 · SAAS · PRODUCT
Sample — B2B Billing Platform Replacement
A 9-month replacement of an internal billing platform. Hybrid: waterfall outer frame, agile inside.
# | Phase | Coordinator's primary task | Key artifact | Next gate / milestone | AI / info-mgmt guardrail
01 | Initiation | Confirm sponsor, success metrics, integration boundaries (Stripe, Salesforce, NetSuite). Set up source-of-truth in Notion + GitHub. | Light charter · Success criteria | Engineering capacity confirmation | AI summaries OK for non-customer notes; never for billing data.
02 | Planning | Backlog seeding, sprint cadence, status template. Identify shared dependencies on platform team. | Backlog · Sprint plan · Roadmap (3 sprints visible) | Architecture review approval | Roadmap in Linear; status writeups in Notion. One source of truth each.
03 | Execution | Sprint coordination. Cross-team dependency tracking. Customer comms drafts. Vendor SDK escalations. | Burndown · Status memo · Defect tracker | Pilot to top-10 accounts | Customer data never in vendor support tickets.
04 | Monitoring | Track pilot KPIs. Defect ageing. Customer-impact escalation rate. Migration readiness by cohort. | Pilot dashboard · Defect SLAs · Cohort tracker | Cohort 2 go/no-go | Dashboards rebuilt from source weekly. No screenshots in steering decks.
05 | Closing | Decommission legacy. Operational handover to billing ops + CS. Capture migration lessons. Customer-success comms close-out. | Runbook · Lessons · CS playbook | Decom sign-off | Old platform DB archived per data-retention policy.

## Gate Evidence
MODULE 02 · SAAS · PRODUCT · GATES
Evidence Required at Each Gate
What the governance body needs in order to make the next decision.
# | Gate | Evidence required | Owner | Status / notes
G01 | Engineering capacity confirmed | Capacity model, roadmap impact analysis, sprint commitment | VP Engineering | Cleared
G02 | Architecture review | ADRs, security review, vendor SDK assessment | Architecture board | Cleared
G03 | Pilot launch | Top-10 customer outreach plan, rollback plan, support staffing | PM + CS lead | Active
G04 | Cohort 2 go/no-go | Pilot metrics, defect trend, NPS impact | Steering | Pending
G05 | Legacy decommission | Data retention plan, customer migration confirmation, audit trail | PM + Legal + Eng | Pending