## Fit Diagnostic
MODULE 05 · BANKING · HYBRID
Sample — Banking Core Modernisation Programme
$140M, 36-month programme. Strong PMO. Multiple agile vendor teams inside a waterfall frame.
# | Question | Lean ← | Score 1–5 | Notes / evidence
01 | How stable is the scope? | Stable=1 → Emergent=5 | 3 | Some scope is regulated and stable; some emerges through integration discovery.
02 | How expensive is mid-flight change? | Cheap=5 → Expensive=1 | 2 | Mid-flight changes hit migration windows — expensive.
03 | How interdependent is the work? | Self-contained=5 → Coordinated=1 | 1 | Highly coordinated with risk, compliance, ops, three vendor teams.
04 | What governance does the environment require? | Lightweight=5 → Heavy=1 | 2 | Heavy PMO. OSFI oversight. Audit committee reporting.
Verdict
| Recommended posture: | Hybrid with waterfall outer frame and agile delivery within vendor workstreams. Coordinator role is heavy translation.

## Failure Spot-Check
MODULE 05 · BANKING · HYBRID
Five Failure Modes — Findings
Findings on this real project.
# | Failure mode | Symptoms — what you'd look for | Y / N | Evidence on this project
01 | Waterfall theatre | Schedule exists but not used. RAID log updated but no one acts. | Y | Two of fifteen RAIDs are stale. Schedule reviewed but not used in last two SCs.
02 | Agile theatre | Sprints, POs, retros — but no real discipline. | Y | One vendor's "sprint" is a 6-week mini-waterfall in costume.
03 | Methodology mismatch | Wrong approach for the work. | N | Methodology fits the work.
04 | Hybrid without translation | Sprint outputs never aggregate up; PMO formats never reach team. | Y | Major translation gap — vendor sprint outputs not formatted for OSFI evidence pack.
05 | Methodology as excuse | "Can't give a deadline because we're agile." | Y | Risk team: "can't commit to dates because of agile cadence."

## Translation Map
MODULE 05 · BANKING · HYBRID
Translation between Agile and Governance
Real artifacts that flow between layers on this project.
# | Source artifact (agile) | Destination format (governance) | Translation owner / cadence
01 | Vendor sprint outputs | OSFI evidence pack | Coordinator + Risk Lead · monthly
02 | Defect ageing | Audit committee dashboard | Coordinator · monthly
03 | Sprint review | Steering committee narrative | Coordinator · monthly
04 | Backlog estimates | Schedule baseline updates | Coordinator + PM · per release
05 | Retro outputs | Programme RAID log | Coordinator · post-retro