## Fit Diagnostic
MODULE 05 · SAAS · PURE AGILE
Sample — Series A B2B SaaS Product Team
22 engineers. Single product. Lean governance. Pure agile is the right fit.
# | Question | Lean ← | Score 1–5 | Notes / evidence
01 | How stable is the scope? | Stable=1 → Emergent=5 | 5 | Discovery-driven product. Roadmap rewritten quarterly.
02 | How expensive is mid-flight change? | Cheap=5 → Expensive=1 | 5 | Code refactor is cheap; mid-flight feature changes are normal.
03 | How interdependent is the work? | Self-contained=5 → Coordinated=1 | 4 | Single product team. Some platform dependencies.
04 | What governance does the environment require? | Lightweight=5 → Heavy=1 | 5 | No PMO. Lightweight governance via founder + VP Eng.
Verdict
| Recommended posture: | Pure agile (Scrum + Kanban hybrid) is appropriate. No need to import waterfall artifacts.

## Failure Spot-Check
MODULE 05 · SAAS · PURE AGILE
Five Failure Modes — Findings
Findings on this real project.
# | Failure mode | Symptoms — what you'd look for | Y / N | Evidence on this project
01 | Waterfall theatre | Schedule exists but not used. RAID log updated but no one acts. | N | No waterfall theatre — no waterfall.
02 | Agile theatre | Sprints, POs, retros — but no real discipline. | Y | Retros have produced the same complaints for 3 sprints with no follow-through. Classic Scrum-but.
03 | Methodology mismatch | Wrong approach for the work. | N | Methodology fits.
04 | Hybrid without translation | Sprint outputs never aggregate up; PMO formats never reach team. | N | Single team, single layer — translation not needed.
05 | Methodology as excuse | "Can't give a deadline because we're agile." | Y | PM occasionally hides from deadline conversations behind "we're agile."

## Translation Map
MODULE 05 · SAAS · PURE AGILE
Translation between Agile and Governance
Real artifacts that flow between layers on this project.
# | Source artifact (agile) | Destination format (governance) | Translation owner / cadence
01 | Sprint review | Investor update narrative | Coordinator · monthly
02 | Velocity & burn | Board deck trend chart | Coordinator + CFO · monthly
03 | Retro action items | Internal engineering OKR list | EM · post-retro
04 | Definition of Done | Customer success readiness | PM + CS · per major release