## Phase Map
MODULE 02 · LIFECYCLE SUPPORT MAP
One Project, Five Phases
For one of your real projects, fill in what the coordinator does at each phase. Use this on Day 1 of any new assignment.
# | Phase | Coordinator's primary task | Key artifact you'd maintain | Next gate / milestone | AI / info-mgmt guardrail
01 | Initiation | Gather essentials. Confirm approval state. Identify sponsors and stakeholders. Find source of truth. | Charter / Stakeholder log | First gate or governance touch | Who can see the charter? Where does it live?
02 | Planning | Set up trackers, cadences, folders, naming conventions. Draft status template. | Schedule / RAID log / Action tracker | Plan baseline approval | One source of truth — not multiple trackers.
03 | Execution | Move actions to owners and dates. Keep issues visible. Vendor follow-up. | Action log / Status report | Major build milestone | Don't paste sensitive vendor info into public AI tools.
04 | Monitoring | Compare actual to plan. Surface decisions. Separate risks from issues. | Variance log / Steering pack | Steering committee decision | Verify any AI summary against trusted sources.
05 | Closing | Confirm action burn-down. Archive. Capture lessons. Hand over to operations. | Closure report / Lessons learned | Service readiness / Post-impl review | Archive controlled versions, not screenshots.

## Phase Checklist
MODULE 02 · SIX QUESTIONS
The Phase Boundary Checklist
Run these six questions at the start of every phase or major handoff.
# | ✓ | Question | Your answer for THIS phase
01 | ☐ | What phase are we in, and what is the next gate, milestone, or review?
02 | ☐ | What evidence does the team need for that decision?
03 | ☐ | Which documents are authoritative — and where is the source of truth?
04 | ☐ | Which actions, issues, risks, and changes need updating now?
05 | ☐ | Who needs an update, approval, or escalation before the next milestone?
06 | ☐ | What must be handed forward so nothing gets lost?

## Role Boundaries
MODULE 02 · WHO OWNS WHAT
Role Boundary Map
Coordination is not authority. Mark each scenario: who owns it, what's your support role.
# | Question / decision | Who owns it | Your supporting role
01 | Approving the project, funding, or major direction change
02 | Day-to-day trade-offs between scope, schedule, and cost
03 | Backlog ordering and product value (Scrum)
04 | Removing impediments and Scrum effectiveness
05 | Logs, follow-up, status packaging, repository discipline
06 | A vendor missing a deliverable date — who escalates
07 | Whether a change request is approved
08 | Whether minutes go out today or tomorrow