## Five Variables
MODULE 07 · PHARMA · CLINICAL TRIAL PLATFORM
Sample — Phase III Clinical Trial Software
GxP / 21 CFR Part 11 environment. Quality cuts are not an option.
# | Variable | What you'd flex first if pressure came | Flex remaining | Already committed | Evidence / notes
01 | Scope | Defer non-essential UI features to post-launch | M | M | Validated requirements are fixed; UX polish is droppable
02 | Schedule | 4 weeks remaining contingency in 18-month plan | H | M | Sponsor accepted full 22% schedule contingency
03 | Cost | $500K reserve untouched after 8 months | H | M | Validation effort under-running estimate
04 | Quality | None — quality bar is regulatory | L | H | GxP, 21 CFR Part 11, ICH GCP — all non-negotiable
05 | Risk | Active management — risk register reviewed weekly | M | M | Two amber items being driven down

## Scope Triple
MODULE 07 · PHARMA · CLINICAL TRIAL PLATFORM
Scope — three kinds, with the gap
Watch the gap between documented scope and what the sponsor actually expects.
# | PRODUCT scope | PROJECT scope (team will do) | SPONSOR'S head
01 | eCRF (electronic case report form) module | Build, validate, train sites | Faster trial enrolment, EU/US regulatory readiness
02 | Patient ePRO module | Build, integrate with eCRF, validate | Real-time patient outcome data for medical monitor
03 | AI-assisted query generation | OUT OF SCOPE per Phase 3 charter | "AI to flag protocol deviations" — sponsor casual mention in board update
04 | Real-world data integration | Out of scope | Future RWD harmonisation hinted in sponsor 1:1 — flag

## Risk Mapping
MODULE 07 · PHARMA · CLINICAL TRIAL PLATFORM
Risk → Variable mapping
For each risk, which of the five variables would absorb it. Plus the absorption strategy.
# | Risk | Variable threatened | Mitigation | Absorption strategy
R01 | Validation re-run if requirement changes mid-build | Schedule + Cost | Strict change-control board | Reject changes; absorb in Phase 4 release
R02 | Site readiness — training schedule slip in 2 of 18 sites | Schedule | Site-specific catch-up plan | Stagger go-live; absorb in schedule (have buffer)
R03 | Vendor SOC 2 audit window conflicts with cutover | Schedule + Quality | Negotiate revised audit timing | Schedule shift OR additional vendor effort
R04 | Statistical computing dependency for ePRO | Cost | Stat group resource confirmed | Absorb in cost contingency if scope grows
R05 | Health Canada inspector availability for pre-launch review | Schedule | Booked 14 weeks early | Re-book; accept 6-week schedule shift if missed

## Contingency Burn
MODULE 07 · PHARMA · CLINICAL TRIAL PLATFORM
Contingency Burn — sample
A project burning contingency faster than it burns work is a project where contingency is about to run out.
# | Month | Schedule original | Schedule used | Cost original | Cost used | Notes
M01 | Month 1–4 | Schedule: 16 wk | 1 wk | $2M | $400K | On plan
M02 | Month 5 | — | 0.5 wk | $2M | $500K | Site readiness slip captured early
M03 | Month 6 | — | 0 wk | $2M | $600K | Strong recovery
M04 | Month 7 | — | 0 wk | $2M | $700K | On plan
M05 | Month 8 | — | 0.5 wk | $2M | $850K | Vendor audit conflict
M06 | Cumulative through M8 | 16 wk | 2.0 wk used | $2M | $850K used | 12.5% schedule contingency consumed; healthy