## Five Variables
MODULE 07 · SAAS · PLATFORM MIGRATION
Sample — Internal Billing Platform Migration
Hybrid project. 9-month delivery. Pressure on cost; quality bar protected for revenue-critical flows.
# | Variable | What you'd flex first if pressure came | Flex remaining | Already committed | Evidence / notes
01 | Scope | Drop reporting modernisation; keep migration core | M | M | Reporting can ship in Q2 next year
02 | Schedule | 3 weeks contingency, mostly intact at month 6 | M | L | On plan; some risk to month 8
03 | Cost | $200K cost contingency unused | H | L | Conservative estimate; vendor under-running
04 | Quality | Test coverage on legacy edge-cases — currently 70% target | M | H | Revenue-critical flows protected; non-revenue flows can flex
05 | Risk | Customer comms risk — moderate; technical risk — moderate | M | M | Two ambers on customer churn signal

## Scope Triple
MODULE 07 · SAAS · PLATFORM MIGRATION
Scope — three kinds, with the gap
Watch the gap between documented scope and what the sponsor actually expects.
# | PRODUCT scope | PROJECT scope (team will do) | SPONSOR'S head
01 | New billing engine (Stripe + custom) | Build, migrate, decommission legacy | Higher MRR conversion, cleaner board narrative
02 | Customer self-service portal | Build, integrate with new engine | Customer NPS lift, lower CS ticket volume
03 | Reporting modernisation | Phase 2 — out of current scope | "Better board metrics by year-end" — sponsor mentioned in fundraising
04 | AI-assisted reconciliation | OUT OF SCOPE | "Maybe we can use AI to find revenue leakage" — founder Slack

## Risk Mapping
MODULE 07 · SAAS · PLATFORM MIGRATION
Risk → Variable mapping
For each risk, which of the five variables would absorb it. Plus the absorption strategy.
# | Risk | Variable threatened | Mitigation | Absorption strategy
R01 | Top-10 customer churn during migration | Cost (in CAC) + Quality (NPS) | Hand-held migration plan; CS lead per account | Defer migration of high-risk accounts; absorb in schedule
R02 | Vendor Stripe API rate-limit changes | Schedule + Quality | Direct vendor escalation channel | Cost increase for higher-tier API; absorb in cost contingency
R03 | Engineering staffing — two devs leaving in Q3 | Schedule + Cost | Rehire in progress; backfill plan | Schedule slip OR scope cut
R04 | Compliance review on data migration | Schedule | Pre-cleared with privacy officer | Re-baseline 1 week if scope grows
R05 | Customer support readiness for new portal | Quality (CSAT) | Training plan + FAQ | CSAT impact 1–2 weeks post-launch — absorb

## Contingency Burn
MODULE 07 · SAAS · PLATFORM MIGRATION
Contingency Burn — sample
A project burning contingency faster than it burns work is a project where contingency is about to run out.
# | Month | Schedule original | Schedule used | Cost original | Cost used | Notes
M01 | Month 1–3 | Schedule: 12 wk | 0.5 wk | $1M | $80K | On plan
M02 | Month 4 | — | 0 wk | $1M | $140K | Vendor under-running
M03 | Month 5 | — | 0 wk | $1M | $200K | Eng dev attrition flagged — replan
M04 | Month 6 | — | 0.5 wk | $1M | $280K | Replan absorbed
M05 | Month 7 | — | 0 wk | $1M | $350K | Top-10 customer migration ongoing
M06 | Cumulative through M7 | 12 wk | 1 wk used | $1M | $350K used | Healthy. ~8% schedule, ~35% cost reserve consumed.